## Sprint 24 Backlog
Issue ID | Feature / Task | Assignee | Story Points | Status | Target Release
PHX-401 | Gmail connector and IMAP search sync | Rahul Patel | 8 | In Progress | v2.4.0
PHX-402 | Local CompanyData manual folder scanner | Dev Team | 5 | Completed | v2.4.0
PHX-403 | Top-5 related files recommendation engine | Dev Team | 5 | In Progress | v2.4.0
PHX-404 | JWT Dev token role-based login screen | Frontend Lead | 3 | Completed | v2.3.9
PHX-405 | Audit log SIEM exporter to Splunk/Datadog | Security Eng | 8 | Backlog | v2.5.0